## Project schedule (Gantt Chart)
| A Hybrid RAG System with Graph Based Context Retrieval | [5 empty] | Project start: | [7 empty] | 2025-09-15 | [18 empty] | `
| Project Manager | Gagan Preet Singh |  |  |  |  | Display week: | [7 empty] | 4
[7 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-10-06 to 2025-11-30
 | time axis 2025-10-06 to 2025-11-30
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Team Formation | Gagan | 100% | 2025-09-15 | 2025-09-22 | 8
| Project Proposal Finalization | Gagan Ram Sourav Divyansh | 100% | 2025-09-22 | 2025-09-29 | 8
| Signed Proposal | Ram | 100% | 2025-09-29 | 2025-10-01 | 3
Foundations
| Review RAG, citation graphs, explainability methods | Gagan Ram Sourav Divyansh | 100% | 2025-10-10 | 2025-10-17
| Finalize system architecture (already drafted, refine for implementation) | Gagan Ram Sourav Divyansh | 100% | 2025-10-10 | 2025-10-17
| Set up Docker, Python venv, ChromaDB, Ollama runtime | Ram | 100% | 2025-10-10 | 2025-10-17
| Configure shared GitHub repo | Ram | 100% | 2025-10-10 | 2025-10-17 | 8
Data Layer
| Implement PyMuPDF + Docling pipeline | Sourav | 100% | 2025-10-17 | 2025-10-30 | 14
| Integrate OpenAlex API, build graph with NetworkX | Gagan | 100% | 2025-10-17 | 2025-10-30 | 14
| Save graph objects for later traversal | Gagan | 80% | 2025-10-17 | 2025-10-30 | 14
Retrieval Layer
| Use sentence-transformer, store embeddings in VectorStore | Ram |  | 2025-10-30 | 2025-11-07 | 9
| Implement top-k traversal, scoring heuristic | Gagan |  | 2025-10-30 | 2025-11-07 | 9
Reasoning & Explainability
| Connect Ollama runtime, build prompt template | Divyansh |  | 2025-11-07 | 2025-11-14 | 8
| Add citation trails, source tagging, tracing tools | Sourav |  | 2025-11-07 | 2025-11-14 | 8
| Implement interactive graph with Plotly | Sourav |  | 2025-11-07 | 2025-11-14 | 8
Interface & Demo
| Upload PDFs, input queries, display answers | Divyansh |  | 2025-11-14 | 2025-11-21 | 8
| Add histograms, graph visualizations | Sourav |  | 2025-11-14 | 2025-11-21 | 8
Evaluation & Optimization
| Explore BLEU, ROUGE-L, BERTScore, hallucination, latency | Ram |  | 2025-11-21 | 2025-11-28 | 8
| Adjust embeddings, graph hops, fusion weights | Gagan |  | 2025-11-21 | 2025-11-28 | 8
Wrap-up & Final Deliverables
| Create S3 bucket, update code for S3 | Ram |  | 2025-11-28 | 2025-12-05 | 8
| Deploy Lambda for PDF upload & parsing | Ram |  | 2025-11-28 | 2025-12-05 | 8
| Containerize app, connect to S3 + Ollama | Ram |  | 2025-11-28 | 2025-12-05 | 8
| Run end-to-end testing, document steps | Gagan |  | 2025-11-28 | 2025-12-05 | 8
Documentation & Report
| Write project report, README, instructions | Divyansh |  | 2025-11-28 | 2025-12-05 | 8
Demo & Presentation
| Prepare slides, live demo, rehearsal | Gagan Ram Sourav Divyansh |  | 2025-12-05 | 2025-12-05 | 1
Formulas:
Display week: = [Display week:, row below]

## Workload Distribution
Week | Phase | Task | Work | Deliverable | Ram | Sourav | Gagan | Divyansh
Week 1–2 | Foundations | Task 1.1 - Literature Review & Design | Review RAG, citation graphs, explainability methods | Design doc + updated architecture diagram | ✅ | ✅ | ✅ | ✅
Week 1–2 | Foundations | Task 1.1 - Literature Review & Design | Finalize system architecture (already drafted, refine for implementation) | Design doc + updated architecture diagram | ✅ | ✅ | ✅ | ✅
Week 1–2 | Foundations | Task 1.2 - Environment & Repo Setup | Set up Docker, Python venv, ChromaDB, Ollama runtime | Working dev environment + “hello world” model | ✅
Week 1–2 | Foundations | Task 1.2 - Environment & Repo Setup | Configure shared GitHub repo | Working dev environment + “hello world” model | ✅
Week 2–3 | Data Layer | Task 2.1 - PDF Parsing & Chunking | Implement PyMuPDF + Docling pipeline | JSON chunks with metadata |  | ✅
Week 2–3 | Data Layer | Task 2.2 - Citation Graph Builder | Integrate OpenAlex API, build graph with NetworkX | Working citation graph visualizer |  |  | ✅
Week 2–3 | Data Layer | Task 2.2 - Citation Graph Builder | Save graph objects for later traversal | Working citation graph visualizer |  |  | ✅
Week 3–4 | Retrieval Layer | Task 3.1 - Vector Embeddings & Storage | Use sentence-transformer, store embeddings in VectorStore | Retrieval by cosine similarity | ✅
Week 3–4 | Retrieval Layer | Task 3.2 - Graph Traversal & Fusion Engine | Implement top-k traversal, scoring heuristic | Ranked retrieval list with confidence scores |  |  | ✅
Week 4–5 | Reasoning & Explainability | Task 4.1 - LLM Response Integration | Connect Ollama runtime, build prompt template | Initial Q&A responses |  |  |  | ✅
Week 4–5 | Reasoning & Explainability | Task 4.2 - Explainability & Tracing Module | Add citation trails, source tagging, tracing tools | Explainable outputs with traceability |  | ✅
Week 4–5 | Reasoning & Explainability | Task 4.2 - Explainability & Tracing Module | Implement interactive graph with Plotly | Explainable outputs with traceability |  | ✅
Week 5–6 | Interface & Demo | Task 5.1 - Streamlit Interface | Upload PDFs, input queries, display answers Show sources, confidence, citation graph. | Functional frontend |  |  |  | ✅
Week 5–6 | Interface & Demo | Task 5.2 - Visualization Enhancements | Add histograms, graph visualizations | Evaluation plots in UI |  | ✅
Week 6–7 | Evaluation & Optimization | Task 6.1 - Metrics Evaluation | Explore BLEU, ROUGE-L, BERTScore, hallucination, latency | Evaluation report | ✅
Week 6–7 | Evaluation & Optimization | Task 6.2 - Hyperparameter Tuning | Adjust embeddings, graph hops, fusion weights | Improved accuracy/latency tradeoff |  |  | ✅
Week 7–9 | Wrap-up & Final Deliverables | Task 7.1 - AWS Setup & Storage | Create S3 bucket, update code for S3 | Code integrated with S3 | ✅
Week 7–9 | Wrap-up & Final Deliverables | Task 7.2 - Lambda Wrapper for PDF Ingestion | Deploy Lambda for PDF upload & parsing | Automated ingestion pipeline | ✅
Week 7–9 | Wrap-up & Final Deliverables | Task 7.3 - Deploy Streamlit via Docker on EC2 | Containerize app, connect to S3 + Ollama | Deployed demo app | ✅
Week 7–9 | Wrap-up & Final Deliverables | Task 7.4 - Testing & Demo Prep | Run end-to-end testing, document steps | Tested deployment + demo guide |  |  | ✅
Week 7–9 | Wrap-up & Final Deliverables | Task 8.1 - Documentation & Report | Write project report, README, instructions | Final_Project_Report.docx + repo |  |  |  | ✅
Week 7–9 | Wrap-up & Final Deliverables | Task 9.1 - Demo & Presentation | Prepare slides, live demo, rehearsal | Final demo presentation | ✅ | ✅ | ✅ | ✅